## Sheet1
Ministry of Energy and Minerals.
Somali Electricity Recovery Project
Project Implementation Unit (PIU)
PRE-BID CONFERENCE
HEALTH FACILITIES - GOVERNMENT OF SOMALILAND - 24 November 2024
ITEM NO. | ITEM DESCRIPTIONS | RESPONSE FROM PIU/MINISTRY | BID REFERENCE
1 | We respectfully request an extension of at least two (2) weeks for the deadline. Given the comprehensive scope of these promising tenders, coupled with extended courier times for international bid submissions and the significant time and effort required to prepare submission documents, this extension would allow bidders to present their most competitive proposals, ensuring optimal value for the employer. | The project is behind schedule and due to that the Ministry can no longer extend the submission deadline. Therefore all bidders are encourage to submit their bids as per the submission deadlines stipulated in the bid document. No further extension granted. | Deadline for submission of bid(ITB 23.1)
2 | Considering the delivery challenges and extended delivery times experienced with courier services like DHL Express and TNT, could we explore the possibility of submitting bids electronically to ensure efficiency and timeliness? | No electronic submissions are accepted. The Ministry shall not take the responsibility of any bids submitted through courier services such as DHL. Only bids submitted physically to the Ministry's offices shall be considered for evaluations. | Form of submission (ITB 22.1)
3 | Given that electronic bid submission is not permitted and financial envelopes are not password-protected, how will the security of financial bids be handled, preventing any premature opening. In the interest of transparency and adhering to best practices, we kindly request that the total bid amount for all submissions be disclosed during the public bid opening. Thanks for your kind consideration in this regard. | The bid is based on the two envelope bidding process which doesn't allow any opening of the financial envelopes during the 1st bid opening stage where only technical bid shall be opened. The security provided is that all financial bids shall be isolated during the 1st opening, put in separate container/box,sealed off, signed and initialled by all the bidders' attendees. When the financial bids for the contractors who proceeded to the second round (financial stages )are to be opened, all the initial provisioned security measured shall be considered and checked. After all, financial bid opening shall occur in the presence of the contractors who have succeedeed to proceed to next stage which is the financial bid. Separate USB for the Technical Bids and the Financial Bid and included in their separate envelopes. | Financial Bid Opening (ITB 26.6)
4 | The tender states “In addition to the above technical personnel, contractor shall also hire security personnel to guard and protect the facility round the clock. Minimum 2 people is recommended for the day and night shifts.” Please confirm that once the contractor has installed/commissioned the sites, the physical security of the assets will be the responsibility of the end-users, and at the same time kindly clarify the role and quantity of the security team. | During the O&M phase, the contractor will be responsible for the facility's security. Security personnel must be assigned to day and night shifts, ensuring that the facility is consistently protected throughout the entire O&M period. | Scope of Works for the Security Personal (RFB Section 3.5.1)
5 | In Section IV - Bidding Forms - ES Management Strategies and Implementation Plans (ES-MSIP) there is a reference to ITB 11.1 (j) of the Bid Data Sheet. - This section does not exist. | Refer to 11.2 (i) | ITB 11.1 (j)
6 | Alternately, please confirm if there is adequate space inside the facilities to install the required inverters, batteries and electrical distribution and protection systems. | Spaces are available. However, it is contractor's obligation to make ground related due dilligence and confirmation on what works for their proposed systems | N/A
7 | Please confirm if there is sufficient space designated for rooftop versus ground-mounted installations at the maternity centers and health center for the required off-grid solar systems, including batteries, inverters, and internal wiring | Spaces are available. However, it is contractor's obligation to make ground related due dilligence and confirmation on what works for their proposed systems | Section VII - Employer’s Requirements/ site visits
8 | Are DC-coupled solutions acceptable, given that they are more cost-effective and energy-efficient compared to AC-coupled solutions, and require fewer energy conversion stages? | Both options are allowed either DC-AC or DC-DC coupling | AC-Coupled system
9 | Kindly provide the coordinates for the 25 sites and 21 sites | This data is available (coordinates will be sharing) | Site Locations
10 | The Bidders are required to attach Award letters and completion certificates for the previous and current projects. We require clarification if both the award letters and completion certificates are required for each project or if either will suffice. | Submission of both the award letters and the completion certificates are required. For the ongoing contracts, award letters suffices.
11 | In the technical evaluation criteria, the detailed design has been allocated 12 marks. Clarify if provision of detailed designs is a mandatory requirement? | It is mandatory and shall be included as part of the mandatory requirement under item 11.2 (i)-(m)
12 | Bidders are required to provide Statutory documents (registration and certification documents), Should the documents be certified by a commissioner of oaths? | Registration and certification documents of eligible countries of Bank financed operations are acceptable.
13 | In technical evaluation, the pass mark for technical evaluation is not provided in the RFB document, we request clarification on the pass mark for the technical evaluation. | Please refer to ITB 32.2. The technical pass score is 70% as indicated in the bidding document. | Technical score pass mark
14 | How does the O&M cost be factored in after the initial 2 years O&M Services. | The quoted price for the O&M services shall remain the same throughout if the contract for the services needs to be extended beyond the currently estimated 2 years. | Operations and Maintenance (O&M) Costs
15 | How is the JV Partnership is being evaluated with regard to their roles | Bidders shall refer to the pages of 58-68 under section III about Evaluation and qualification criteria | Contractors associations
16 | Is it permissible to submit quotes for specific facilities rather than for the entire lot? | No, it is not allowed. The entire lot must be quoted as a whole; sectionalized bidding is not permitted. | N/A
17 | In the battery section of the tender it is required to use lithium iron batteries, but the ESMP document requires lead acid batteries. Please clarify which battery to use | Follow the specifications and requirement as stipulated in the bid specifications and GTP. | Technical part
18 | which document will prevail, Bidding document or ESMP, if there is conflict? | ESMP is part of the bid document. Comply each as requested for. | Technical part
19 | Where are distribution boxes used? For PV system inside loads or for the customer side? Are there any requirements for the capacity and number of circuit breakers in it? | Both on PV side and on the customer side for further downstream distribution of power to load centers | Technical part
20 | How many output line from the system to load side? | Different sites pose different requirement. However, it is the duty of the successful bidder to show in its design on the number of out-goers to the load centers which shall be subject for approval by the4 project team. | Technical part
21 | Please confirm the distance from the PV system to the load, and who will provide this section of cable? | Distance shall be proposed by the bidder since the detail design is to be undertaken by the bidder. All cables is in the current scope of this bid. | Technical part
22 | What’s the explicit proof on the quality of spare parts and maintenance services mentioned in criteria? What kind of documents should we provide? | Refer to ITB 11.2 - (f),(g),(h),(i),(j),(k). | Bid data sheet ITB 32.2 Category II 2.5 “Quality of mandatory and recommended spare parts and maintenance services
23 | What detailed information should we provide in this document? | Go through employer's requirement under Operation and Maintenance requirement to understand in depth about client expectation | ITB 32.2 Category II 2.6 “Detailed Operational and Maintenance Plan for the Project”
24 | What is the Grievance redress mechanism for? For forced labour? For bidding procedure?.... | Take note on the provisions of ESMP especially under item 6.4 | Bid data sheet ITB 11.2 s) Grievance redress mechanism
25 | “The particulars and catalogue numbers of the proposed equipment shall be highlighted.” We are not very sure about the particulars and catalogue numbers, would you please explain them? | Various equipment always are alloted part numbers or catalogue numbers by the manufacturers. These part numbers shown in the data sheet is what need to be highlighted for submision. | Bid data sheet ITB32.2 l) Technical data sheet (brochures, catalogues, drawings) describing in detail the offered items. The particulars and catalogue numbers of the proposed equipment shall be highlighted.
26 | Since roofs are mostly four-sided sloped roofs with a small usable area, and not sure about the type of color steel tiles, is it acceptable for all PV structures to be in the form of ground mounting? If no, please provide us the type of color steel tiles and size of usable surface. | Both roof and ground mount are allowed. It is the bidders' responsibility to find out and present in their design what best can work for the respective facilities. | Section VII employer’s requirements-2.3.8 Distribution boards
27 | Do we need to supply the lighting system (lamp, socket, switches), if the answer is yes, then, how many? And what kind of? | For places where such systems are missing. For how many and kind is subject for bidder's design | Section VII employer’s requirements
28 | Please estimate the cable length inside the buildings and along the buildings in these three kinds of health centers. | Subject for bidders design | Section VII employer’s requirements
29 | Is it required to have Tax compliance certificate by bidders | Yes and its Mandatory. Shall be submitted as part of the Mandatory requirement.
30 | "A firm acting as a Bidder, whether individually or as part of a joint venture (JV), may not participate in more than one Bid, except in cases of permitted alternative Bids. Any such involvement will lead to the disqualification of all Bids associated with the firm. However, this restriction does not apply to a Bidder participating as a subcontractor in another Bid or to a firm serving as a subcontractor in multiple Bids" | Bidders may participate in the Tender either as sole bidders or as members of a joint venture but are not permitted to join more than one bid as part of a joint venture. However, a firm may act as a subcontractor in multiple bids. Bidders are also allowed to submit bids for multiple lots, with no restrictions on the number of lots they can pursue. | ITB 4.3
31 | It is no problem for us to have the needed Manufacture’s Authorizations. However, it will be very difficult, if not impossible, to get manufacturers to commit to the referenced clause 27 in the authorization form. This specific clause defines the warranty of the contractor rather than a product warranty. Not only doesn’t a manufacturer have an influence on the contractor’s work, but what is also needed is the statement of warranty for his own product. We therefore propose to have the manufacturer refer to its own warranty, rather than the contractors (overall) warranty. | Kindly stick to the requirement. The warranty shall remain as shown in clause 27 of the conditions of the contract. | Manufactures Aithorization
32 | Please explain to us the this requirment as indicated item (c) in the note section of the heath and safety requirements for the O&M stage. What are the bidders expected to submit. | Item (c) refers to the PPE including to the protective clothing and other related safety clothing necessary for undertaking any electrical works by contractor's employees. It is requirement all these to be taken into account for O&M costing purposes. | Health and safety requirments for the O&M Stage
33 | We are in the process of submitting the below two tenders: 1. RFB No.: SO-MOEM-445067-CW-RFB and 2. RFB No.: SO-MOEM-445077-CW-RFB. with the first requiring a turnover of $2.9 million and the second requiring $2.7 million. We would like to request clarification on how the turnover requirements will be evaluated, Specifically, we seek to understand whether the turnover for each tender will be considered separately, requiring our company to meet the individual turnover thresholds of $2.9 million and $2.7 million respectively, or if the cumulative turnover (2.9 + 2.7 = $5.6 million) should be met by the company submitting the 2 tenders? | regarding the turnover requirements for the two tenders: RFB No. SO-MOEM-445067-CW-RFB, which specifies a turnover requirement of $2.9 million, and RFB No. SO-MOEM-445077-CW-RFB, which specifies a turnover requirement of $2.7 million. We confirm that these are two separate tenders and will be evaluated independently as outlined in the respective tender documents. Accordingly, the turnover for each tender will be considered separately. This means that your company must demonstrate a turnover of at least $2.9 million to meet the requirements of RFB No. SO-MOEM-445067-CW-RFB, and a turnover of at least $2.7 million to meet the requirements of RFB No. SO-MOEM-445077-CW-RFB. The turnover thresholds cannot be combined; each tender must meet its specific turnover requirement separately. | Section III: under Evalaution and qualification 2. Qualifications
34 | As part of our efforts to make technical proposal for health facilities site across Somaliland, and Current challenges in conducting assessments at every site due to logistical constraints, we kindly request further clarification regarding the preliminary design reports. Specifically, could you provide a detailed example like the one from your presentation for the education sector? A design approach from the Ministry of Energy that covers all technical aspects | This is it is contractor's obligation to undertake due diligence on site conditions for their proposed systems, and find any information that may be necessary for preparing their bid.
35 | How many sites are designated for rooftop installations versus ground-mounted systems? | The bider is advised to visit and invistigate the site where the plants is to be installed and its surroundings and obtain for itself on its own responsibilities all information that may be necessary for preparing the bid and entering into a contract for the provision of plant and installation services. The costs of visitning the site shall be at the bidder's own expenses. | 7.2 Clarification of bidding documents, site visit pre-bid meeting
36 | As we review the partnership structure for the proposed joint venture,. Specifically, we seek clarification on the financial and operational arrangements between the lead and local partners. Could you please confirm the percentage allocation for the joint venture between the lead partner and local partners? | All members of a joint venture (JV) share equal responsibility for completing the contract, and this must be clearly stated in the JV agreement. However, evaluation depends percentage the lead member usually handles 40-50% of the project, while the other members often take on 20-30%. | Section III - Evaluation and Qualification Criteria
37 | Could you please clarify which party, between the lead partner and the local partner in the joint venture, is responsible for obtaining and providing the manufacturer's authorization? | The bidder is to provide the Manufacturer’s Authorization. | ITB 4 and ITB 5 .
38 | seek clarification regarding the bid validity period. It is mentioned that the bid validity is 120 days; however, the specified deadline extends until February 28, 2025, which seems to exceed the 120-day limit. Could you please confirm if there is an extension to the bid validity or provide further clarification on this matter? | As per ITB 19.1 of the Bidding Data Sheet (BDS), the bid validity is set for a period of 120 days, until February 28, 2025. | Refer ITB 19.1
39 | Please kindly clarify if the submission requires the original bids of completion along with “Copy 1” and “Copy 2,” or if certified copies of these documents would be acceptable? | The submission document will be the number of copies is: Two (2) copies (hard copy) and a soft copy in a flash disk each for technical and financial - with a password; all enclosed in separate envelopes marked as ‘’Original” and “Copy 1’, COPY 2‘’, and a soft copies in a Flash Disks | ITB 22.1: Submission and Opening of Bids
40 | · Please specify the venues and locations for the of the technical parts and financial public opening of the bids involved in this process | Bid opening will occur at the Project Implementation Unit (PIU) Office, Ministry of Energy and Minerals, Mujahid Lixle Rd, next to the Ministry of Commerce. | Public Opening of Technical Parts of Bids /ITB 26.1
41 | Please specific the SCADA system operate as a centralized master system or as independent site-specific systems.? | Health facilities' solar systems can connect to a central SCADA master unit or operate independently at specific sites, with each site. | Technical Requirment
42 | What is the exact amount and currency for the bid security, as specified in Section II - Bid Data Sheet (BDS) (referencing ITB 20.1)? | As, ITB 20.1 indication A Bid-Securing Declaration SHALL BE required. Ann see the Section IV – Bidding Forms 118 | ITB20.1
43 | Could you kindly clarify the specific weight assigned to technical evaluation criteria in relation to financial evaluation criteria during the bid scoring process | Technical evaluation criteria in relation to financial evaluation criteria during the bid scoring process .Technical factors have a total weight of 70% (ITB 32.2), while financial factors have a weight of 30% | Evaluation of Technical Bids (ITB 32.2) and Financial Bids (ITB 36.1)
44 | Please provide the input and output power of the transformer at each Installation point. | This tender does not include a transformer | N/A
45 | Please provide the distance between the master control box and the installation location at each installation point.? | It is the contractor's responsibility to design this and take the necessary steps for installations
46 | For the 'Historical Non-Performance' section in the Request for Proposals (RFP) submission form, should it be left blank if the bidder has no history of non-performance? Or is it mandatory to explicitly indicate 'None' or 'Not Applicable' to comply with the submission requirements?
47 | For a Joint Venture (JV) agreement required as part of the RFP submission, should the agreement be presented as a formal notarized document, or would a letter of intent signed by all parties suffice at the proposal stage? | At the proposal stage, a Letter of Intent signed by all JV members is suffices. However, the letter must outline the intent to enter into a formal agreement and detail the roles and responsibilities of each member as required under Section I (ITB). A formal notarized JV agreement is typically required at the contract award stage. | Section I – Instructions to Bidders (ITB 11.5)
49 | the Manufacturer’s Authorization, should it be obtained and submitted by the lead member of the JV, or is it required from all JV members? | Manufacturer's Authorization as part of the technical bid submission. While it does not explicitly state that the authorization must be submitted by the lead member of a JV, the general responsibility of the lead member is to act on behalf of all members. | N/A
50 | For the Completion Certificates required as proof of past performance, does the RfB mandate submission of original certificates, or are copies (certified or otherwise) acceptable for compliance? | Bidders must provide the contract description and value, copies of completion certificate and names and addresses of clients (who shall be contacted for further information of these contracts in each of the works given). | Section II – Bid Data Sheet (BDS) ITB 11.2(e)
51 | Could you confirm the exact location and format (physical or virtual) of the bid opening, and provide details on how bidders can attend? | The bid opening will take place at the PIU Office of the Ministry of Energy and Minerals Mujahid Lixle Rd, Next to the Ministry of Commerce, 26 June District, in Hargeisa Somaliland. The bid opening is scheduled for December 12, 2024, at 11:00 am Hargeisa Local Time. The bid opening will be physical, and no virtual attendance. | Section II - Bid Data Sheet (BDS) ITB 26.1
52 | What type of bid security is required (e.g., bank guarantee, bid bond, or another form), and are there any specific formatting or issuing institution requirements that must be adhered to? | the bidder must submit a Bid-Securing Declaration as part of the Technical Part of their bid. | Section II - Bid Data Sheet (BDS) ITB 20.1
Note on A1: these two similar question above which indication ,70,71 Question are including above content -Ahmed Hassan

## Sheet2
Ministry of Energy and Minerals.
Somali Electricity Recovery Project
Project Implementation Unit (PIU)
PRE-BID CONFERENCE
HEALTH FACILITIES - GOVERNMENT OF SOMALILAND - 24 November 2024
ITEM NO. | BID REFERENCE | ITEM DESCRIPTIONS | RESPONSE FROM PIU/MINISTRY