## Sheet1
Ministry of Energy and Minerals -JSL
Somali Electricity Recovery Project
Project Implementation Unit (PIU)
PRE-BID CONFERENCE
EDUCATION FACILITIES - M.jeh, Awdal, Sahil, Togdher, Sanag - Somaliland - 23 February2025
ITEM NO. | BID REFERENCE | ITEM DESCRIPTIONS | RESPONSE FROM PIU/MINISTRY
Clarifications
1 | Deadline for submission of bid(ITB 23.1) | We are requesting a 30-day extension to submit a detailed proposal that meets your high standards. A site visit to Hargeisa is necessary to gather with the preparation of detailed technical designs and the local factors required for the preparation of the project costs for a cohesive and well-structured offer. | Due to the constraint assignment's timeframe, the ministry regrets that it is unable to grant any further extension to the original bid submission deadline. We strongly encourage all bidders to ensure that their bids are submitted by the specified deadline, as stipulated in the bid document.
2 |  | After revising the tenders of lot 1 and lot 2, we failed to find the coordinates as described in the Employer's Requirements. Please send us the coordinates along with the site pictures so that we can provide a more integral and specific bid | The site coordinates will be shared with the bidders. However, we strongly encourage all the bidders to undertake the site visit in order to assess the site conditions and any other necessary requirements.
3 | Page (162 )Lot 1 Bid documents | In the tender of lot1, shown in the Table 2: Scope Details: item no.13 and 14, we'd like to know if there's a mistake about the inverter size. As per our understanding, the pv size and inverter size should be the same, for item 13 both should be 22kw and for item 14 both should be 8kw, which is in compliance with the price schedules listed in the Section IV- Bidding Forms. | The Ministry confirms that the inverter sizes listed in the tender of lot 1 as depicted in table 2; for items 13 and 14 are accurate as per the project site specific requirements considered during the preliminary design. Therefore, we encourage bidders to ensure that their bid aligns with the specifications stipulated in the tender documents, including the price schedules in Section IV - Bidding Forms.
4 | Page (159) | Is there any technical specifications for this project. | Please refere the technial specification in section (VII) "Employer Requirements"
5 | JV Outhorsition (ITB21.3) | In the case of a Joint Venture (JV), the Bid must be signed by an authorized representative of the JV on behalf of all members, ensuring it is legally binding. This must be evidenced by a power of attorney (PA) signed by the legally authorized representatives of the JV members. Does the required PA need to be notarized? If so, what is the proper procedure for obtaining an acceptable notarized PA if one of the JV partners is based outside Somaliland? Kindly clarify. | Yes, the power of attorney must be notarized to ensure its legal validity. Procedure for Notarizing the PA (if one JV partner is based outside Somaliland): Notarization: The PA must be signed by the authorized representative of the foreign JV partner and notarized in the country where the partner is based. Authentication/Apostille: If the foreign country is a signatory to the Hague Convention, the notarized PA should be apostilled. If not, the PA must be authenticated through consular legalization by the nearest Somaliland embassy or consulate. Translation: If the PA is in a language other than English, a certified translation must required.
6 |  | Does the lead company act as a bidder? or the bidder will be JV Name? | "According to the World Bank Procurement Regulations for IPF Borrowers (September 2023): Joint Ventures (JVs) as Bidders (Paragraph 5.38): Firms participating in Bank-financed contracts may form joint ventures with domestic and/or foreign firms to enhance their qualifications and capabilities. A joint venture may be for the long term (independent of any particular procurement) or for a specific procurement. All partners in a joint venture shall be jointly and severally liable for the entire contract​. Bidder Name in a Joint Venture: If a JV submits a bid, the JV itself is considered the bidder, not just the lead company. The JV must identify all partners in the bid, and all members must meet the qualification criteria collectively. Lead Company’s Role: The lead company may be designated to represent the JV, but it does not act as the sole bidder. The entire JV is treated as the bidder, and all partners remain jointly responsible. Thus, the bidder will be the Joint Venture (JV) name, not just the lead company."
7 |  | We need accurate data on the consumption of Education facilities, but this data is not available. Will you require us to conduct new assessments to determine the consumption ofEducation? | In the preliminary design at the bid stage, let bidders use the provided capacity for both PV system and BESS. However, we strongly encourage all the bidders to undertake the site visit in order to assess the site conditions and any other necessary requirement
8 | Section III - Evaluation and Qualification3.1 Financial Capabilities and Form FIN – 3.1 Financial Situation | As per the instructions of the RFB, audited financial statements of the of the last five years to be submitted. Else where in the instructions mentioned that years as 2019-2023, so why its be 2020-2024? | If the tender is published in mid-2024, the requirement for "audited financial statements of the last five years" should refer to the most recent period available. The instructions indicate 2019-2023, suggesting completed financial years are expected. However, if the 2024 audit is finalized in time, 2020-2024 may also be acceptable. To clarify, it's best to confirm with the issuing authority (RFB) whether they strictly require 2019-2023 or would accept 2020-2024
9 |  | As for the past contracts that a bidder achieved, is it evaluated based on their capacity or value | The evaluation of a bidder’s past contracts is based on both capacity and value, as stipulated in the qualification criteria. Bidders are advised to refer to Sections 4.1, 4.2(a), and 4.2(b) of the qualification requirements, as stipulated in Section III – Evaluation and Qualification Criteria, for detailed guidance on the required experience and financial capacity
10 |  | The discount issue expressed in the BoQ is Not clear. Is on our side or the employer side. | Please Refer the ITBs 17.1 in BDS, 17,10, 17.11, 33.4, 33.5, 33.7, 36.1, 36.5, and letter of bid under section IV bidding forms
11 |  | Is It needed to provide simulation reports with the preliminary design? | Yes, it is generally not necessary to provide simulation reports with the preliminary design at the bid stage. What is typically required is a detailed preliminary design that outlines the key system components, their functions, and how they will be integrated. The focus should be on demonstrating that the design concept is feasible, meets the specified requirements,
12 |  | Is the system on-grid, off-grid, or hybrid? | The systems will be Hybrd/off grid of the photo voltaic solar power plants with battery energy storage systems to ensure reliable power supply to the loads.
13 |  | What is the loading power for this system so we can check compatibility with the inverter/PCS system? | The maximum required load capacity for each site along with the corresponding inverter capacity, has already been provided as stipulated table 2 in section VII of the employer requirement. Therefore, the bidder only requires to take into account the preliminary design and proceed the detail design calculations.
14 | in Section IIV Employer Requirements Table 2 | What battery storage system power do they need (in kWh)? | The bidder shall refer the the required battery storage systems as stipulated in section VII at table 2 of the employer requirement.
15 |  | Does the system require the PV arrays to be combined/integrated? | The requirement for combining or integrating the PV arrays depends on the proposed system's PV array design. The design approach should align with the overall system specifications and performance requirements.
16 | Section III - Evaluation and Qualification Criteria forms | According to Section III - Evaluation and Qualification Criteria，4.2（b）specific experiences requires the same experiences as 4.2（a），so why is it necessary to use the form4.2（b）？isn't the form 4.2（a） enough？ | The bidder must have completed at least three contracts in the past five years, with two valued at USD 332,983 each. They must also have completed three solar PV projects, two with a capacity of 100 kWp or more, and one over 10 kWp. Additionally, at least two projects must include Battery Energy Storage Systems (BESS).
17 |  | Are all the schools covered by mobile networks to allow for monitoring and seamless communication? | Yes, all schools are generally covered by mobile networks for monitoring and communication. However, some areas may have weaker network connectivity, and solutions will be explored for those locations.
18 | Section IV - Bidding Forms | Is a bid bond required, and if so, what percentage is mandated? Should it be provided by a bank or an insurance company? | This RFB is applicable for Bid Security Declaration
20 |  | . Is Premier Bank included in the list of preferred bankers? | There are no Prefered Bank in the project.
21 |  | What is the maximum advance payment guarantee, and is it a requirement for advance payments? | The bank Guarantee is to provide when agreed the advance payment. There is no minimum or maximum. However, Advance Payment Guarantee is Mandatory for World Bank-financed contracts. No fixed maximum limit, but the amount is based on mobilization needs. Must be backed by a financial guarantee from an acceptable institution
22 |  | How will the government ensure safety and security during installation and operations and maintenance? | The bidder will acquire workers and handle installations; however, the responsibility for political risk is not explicitly stated. It is hoped that the government will assume liability for such risks, as it typically holds responsibility for political stability and related contingencies affecting the project.
23 |  | In case of any vandalism, how will that be handled? Who is liable for vandalism? | In the case of vandalism, the contractor is liable for vandalism, with repairs possibly covered by the contract
24 | Section VII - Employer’s Requirements (Page193) section 3.1 | What scope should the insurance cover within the project implementation and O&M phases? | It is mandatory that the successful contractor for the Supply and installation of the Solar PV Plant system shall be the one to handle the implementation of the 2-year O&M plans for the lots being awarded. Any opts of undertaking the O&M scope shall disqualified.
25 |  | The bidder will acquire workers and handle installations, but it is not clear who assumes responsibility for political risk. Who bears this liability? | The bidder will acquire workers and handle installations; however, the responsibility for political risk is not explicitly stated. It is hoped that the government will assume liability for such risks, as it typically holds responsibility for political stability and related contingencies affecting the project.
26 | Section VII - Employer’s Requirements (Page165) | Is there a preference for three phase systems rather than single phase? | The preference for three-phase systems over single-phase systems depends on the size of the system
24 | Section III - Evaluation and Qualification Criteria | Can you provide more details on what constitutes "similar nature and size" in regards to previous Solar PV plant projects | Relevant experience includes previous and ongoing Solar PV plant projects of comparable scope and scale within the last five (5) years. Specifically, this refers to the requirements outlined in the Evaluation and Qualification Criteria, Sections 4.2(a) and 4.2(b)
25 | Instrction to Bid(ITB.4.8) | Given that the foreign solar company is the primary contractor for this project, with the local company serving as a subcontractor at the country level, would it be possible for the local Somaliland company to issue a letter of association signed by them?" | If the two companies are not in JV, and the local company serving as a subcontractor, is not required to issue a letter of association. Instead, the bidder should complete the Subcontractors Form as per the requirements. in the Bidding Forms
26 | Section VII - Employer’s Requirements | Given the size of the systems, is there a preference for containerized solutions? If so, on what equipment? | No specific preference for containerized solutions. However, the proposed solutions by the bidder must ensure the optimal system performance, efficiency and compliance with the specifications as stipulated in the employer requirements.
27 |  | How are you calculating the Minimum average annual turnover in Solar Energy Sector per 3.2 of financial requirements? | The minimum average annual turnover is calculated based on the bidder’s total certified revenues from completed or ongoing contracts in the Solar Energy Sector over the specified period. For Lot 1 and Lot 2, the required turnovers are USD 1.3M and USD 952,422, respectively. This is determined by summing the certified payments received for relevant contracts over the last five (5) years and dividing by the number of years considered, as outlined in the financial requirement
28 | Instruction to Bid (ITBS From 4.1 to 4.10 and (ITB 11.2 in Bid Data Sheet | How is the JV partnership being evaluated in terms of their roles? If the JV is based outside the country, should it be registered within the country? From Ministry of Trade and Tourism of the Republic of Somaliland". | As per ITB Sections 4.1 to 4.10, all bidders, including JV and single-entity, local or international, must submit the required documents listed in ITB 11.2 as part of the Technical Section of their bid. JVs based outside Somaliland must comply with local registration requirements from the Ministry of Trade and Tourism of Somaliland or the relevant authority in their country of origin.
29 |  | 2 Years (O&M) Services | During the 2-year Operation and Maintenance (O&M) period, the contractor is responsible.
30 | Section VII - Employer’s Requirements (Page213) section 3.6.9 | Please clarify the after-commissioning contract. | During the 2-year O&M period after commissioning, the contractor must ensure 95% uptime of the plant to meet the proposed CUF at the end of each year. Any maintenance, repairs, or overhauling of the DC area of the SPV system should be performed during nighttime or off-peak hours to avoid any generation loss during the day.
31 | Section VII - Employer’s Requirements (Page167) section 2.3 | As for the plant equipment, there is a lot of certification and grantee certificates which is too difficult to find at this stage, what about if you provide the IEC or INSO certification at the time? | The critical components of the solar plants include Solar PV Modules, mounting structures, PV/String inverters, Battery Inverter/Chargers, switchgears, breakers and fuses, DC and AC cables etc Refer Bid documents
32 | ITB11.2 IN BDS | did you say TCC will be required from all bidders? if yes, what about the international bidders? | Yes, a valid Tax Compliance Certificate (TCC) is required from all bidders. This requirement applies to both local and international bidders to ensure compliance with tax regulations as outlined in the bidding documents in (ITB 11.2
33 |  | The ES/SH expressed in the Bid forms is expressed as an option of either but they are both required in the employers expectations. Kindly elaborate 4.Is the quotation inclusive of operation and maintenance for 2 years? | Yes, the quotation is inclusive of operation and maintenance (O&M) for a period of 2 years. This includes all services necessary for the smooth operation and maintenance of the system, ensuring its efficiency and performance over the duration of the contract. The O&M services cover regular inspections, troubleshooting, repairs, and any necessary replacements of components to maintain optimal functionality.
34 |  | e. The Bid-Security is given as an option of Bid security declaration. Then late on in the Bid document it not an option kindly explain. | The Bid Security Declaration is a mandatory requirement. All bidders must complete and sign the Bid Security Declaration Form as specified in the bid documents
35 |  | how will the employer make payment to international bidders if they win who dont have local bank accounts? | The employer accepts payments to international bidders via their bank accounts, as long as these accounts have a valid SWIFT code for international transactions. This applies to all international bidders, regardless of whether they have a local bank account.
36 |  | The entire project will be awarded to L1 only or can be partially awarded to L2 | Both lot 1 and Lot 2 will be evaluated and contracted independently.
37 |  | Can the capacities of all facilities be combined to meet the required project capacity of 100 kWp? | The required project capacity of 100 kWp cannot be achieved by combining multiple smaller systems. However, a single system with a capacity exceeding 100 kWp, incorporating battery storage, and designed as an off-grid, grid-connected, or hybrid system, will be considered in accordance with the specific experience of 4.2
38 | Section VII – Employer’s Requirements(page 168) | RFID tags are required on each solar panel, but no specifications for the tags have been provided. Should we use Ultra High -Frequency, high-frequency or low-frequency RFID tags, and is an RFID reader required as part of the project? | An Ultra High Frequency RFID tags are recommended due to their longer read ranges and efficiency in asset tracking. Each PV module shall have a Radio Frequency Identification (RFID) tag and it should be weatherproof to withstand harsh environmental conditions.
39 | Section VII – Employer’s Requirements(page 168) | Please clarify the battery cycle requirements, as the GTPS and the design scope cycles at Depth of Discharge (DOD) differ | The Depth of Discharge (DOD) for the Battery Energy Storage System (BESS) shall exceed 95%. This means that the system is designed to regularly utilize over 95% of its total battery capacity during each charge-discharge cycle. As a result, the system is expected to provide a battery life cycle of more than 5000 cycles at this 95% DOD.
40 |  | In grid environments with power quality challenges, transformer-based inverters are recommended; however, they do not have built-in surge protection. Can external surge protection be used on the inverter/charger while having built-in surge protection on the AC-coupled grid-tie inverter? | Yes, external surge protection can be used on the inverter/charger in off-grid and hybrid solar systems, even if the AC-coupled grid-tie inverter has built-in surge protection. It's recommended to install surge protectors on both the AC and DC sides of the system for optimal protection, especially in environments with poor power quality or surge risks. Ensure the surge protector’s voltage and current ratings match your system’s specifications.
41 | Section IIV Employer Requirements Table 2 | Are we allowed to supply a bigger inverter than the one listed? For,example supplying 5kW in place of the 3kW | As per the RFB requirements, the inverter specifications must match those listed.
42 | Employee Requirement | Who carters for the wiring rehabilitation costs? | The wiring rehabilitation costs are the responsibility of the contractor
43 |  | For international companies, is it necessary to have local registration and tax clearance in Somaliland, or would documents from their country of origin suffice? | No, it is not necessary for international companies to have local registration and tax clearance in Somaliland. Documents from their country of origin would suffice.
44 | Employee Requirement | As Advanced Prime Logistics, we will be acting as a subcontractor or association partner to the international solar company, providing full logistics support. In this case, do we need to adhere to the same requirements as the Joint Venture or, since our involvement is solely for logistics support, is it sufficient to provide a letter of association? We would like to confirm that submitting this letter will not negatively impact the evaluation process. | As Advanced Prime Logistics, acting as a subcontractor or association partner providing logistics support to the international solar company, you typically would not need to adhere to the same requirements as the Joint Venture (JV) itself. However, it is a Contractor Responsibilities