## Sheet1
MINISTRY OF ENERGY AND MINERALS (2024)
Annual Work Plan Priorities for 2024
No. | 1. PLANNING DEPARTMENT |  | QUARTER I |  |  | QUARTER II |  |  | QUARTER III |  |  | QUARTER IV
| Objective |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Conducting launching validation meeting of 5-year Strategic plan of MoEM. | bar: Jan
2 | Develop Concept note for Donors, Investors & Moem's partners for Resource Mobilization. | bar: Feb to Apr
3 | Developing Internal 3 year Strategies plan for Energy, Mineral and Petroleum. | bar: Apr to Dec
4 | Developing Monitoring and Evaluation Framework and Research tools. | bar: Apr to Jul
5 | Review Policies of the Ministry for their Implementation Plans | bar: Sep to Dec
NO. | 2. MINING DEPARTMENT |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objectives |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Review and Translation of Regulations English to Somali | bar: Jan to Sep
2 | Exploration Project on Somaliland’s Mineral Resources | bar: Jan to Jun
3 | Conducting Somaliland Mining Sector base-line assessment survey | bar: Apr to Jun
4 | Conducting Somaliland Mining (Minerals) Showcase Events. | bar: Jul to Sep
5 | Finishing and Implementing the Database of the Mining Registration System | bar: Jan to Apr
6 | Developing Gemstone Center & Enhancing Laboratory Center | bar: Mar to Aug
7 | Formalization of Artisinal Miners | bar: Sep to Dec
NO. | 3. ENERGY DEPARTMENT |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objectives |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Review Somaliland National Energy Policy and Finalize Act | bar: Jan to Apr
2 | Conduct Renewable Energy and Electricity Supply Providers (ESP's)Event | bar: May to Jun
3 | Conduct the Energy and Extractives Forum | bar: Jul to Sep
4 | Enhance Renewable Energy Resources Adaptation (Wind, Solar, Geothermal Potential) | bar: Jul to Dec
5 | Develop Electrical Building Installations Guideline and Solar PV Regulation | bar: Jan to Apr
No. | 4. PETROLEUM DEPARTMENT |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objectives |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Finalize of the legal framework for upstream Petroleum | bar: Jan to Jun
2 | Develop Data Resource Management and Data Marketing | bar: Mar to Dec
3 | Monitoring Community Development Programs | bar: Mar to Sep
NO. | 5. HRM DEPARTMENT |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objectives |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Develop a comprehensive Capacity-building guideline | bar: Jan to Mar
2 | Create a Job Description Booklet for all MoEM staff | bar: Apr to Jun
3 | Establish and Develop Health and Safety Procedures | bar: Jul to Sep
4 | Establish Ministry Staff Handbook | bar: Oct to Dec
No. | 6. ADMIN AND FINANCE DEPARTMENT |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objective |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Improving the security and surveillance system in MOEM HQ compound. | bar: Jan
2 | Digitalization of finance system | bar: Feb to Mar
3 | Supplier/contract management | bar: Feb to May
4 | Preparing effective and efficient finance and procurement systems | bar: Jun to Sep
5 | Asset utilization and re-evalution | bar: Sep to Dec
No. | 7. PUBLIC RELATIONS DEPARTMENT |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objective |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Produce News articles, online and print media, Television and radio show on success stories of the Ministry. | bar: Jan to Jun
2 | Updating MoEM Websites. | bar: Jan to Mar
3 | Produce quarterly Magazine for Mineral, Energy and Petroleum. | bar: Jul to Dec
No. | 8. ICT DEPARTMENT |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objective |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Changing the server windows and installing the latest antivirus which is equivalent to the firewall | bar: Jan to Jun
2 | Reducing and Simplifying Internal Publications | bar: Jul to Dec
No. | 9. LEGAL AFFAIRS |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objective |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | National Mining Policy finalized | bar: Jan to Feb
2 | Petroleum Revenue Bill | bar: Mar to Apr
3 | Translate the 18 Mining Regulations. | bar: Apr to Sep
4 | Amendment of the Electricity Act | bar: Aug to Oct
5 | Somaliland National Energy Policy | bar: Apr to May; Nov to Dec
NO. | 10. INTERNAL AUDITOR |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objectives |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Preparing Manual procedures of Internal Audit | bar: Jan to Apr
2 | Implemantation of Internal Audit Plan | bar: May to Aug
3 | Operational Auditing of departmental procedures for the projects in quarterly | bar: Sep to Dec
No. | 11. REGIONAL COORDINATOR |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objectives |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Coordinating and Preparing a facilitation service for all Regional Offices and the Headquarter Activities at MoEM
2 | Conducting data collection on regional ministry activities and staffs | bar: Mar to Jun
3 | Promote coordination and collaboration among Ministry departments, companies, and stakeholders in the regions. | bar: Jun to Dec
NO. | 12. GENDER OFFICE |  | Jan: QUARTER I; Apr: QUARTER II; Jul: QUARTER III; Oct: QUARTER IV
| Objectives |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Develop a Capacity-Building Gender Analysis Frameworks | bar: Jan to Mar
2 | Collaborations with MoEM on Review of gender policy | bar: Apr to Jun
3 | Conduct Workshop on Empowering Gender (MoEM) | bar: Jul to Sep
4 | Development of tools, gender mainstreaming in energy and mineral projects. | bar: Oct to Dec